## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | Creating my own online book shop | #N/A | #N/A | #N/A | #N/A | #N/A
6 | Publishing a book in a shop | #N/A | #N/A | #N/A | #N/A | #N/A
7 | Removing a book in a shop | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | Viewing a books' infomation | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Viewing comments towards a book | #N/A | #N/A | #N/A | #N/A | #N/A
11 | Blocking user's account | #N/A | #N/A | #N/A | #N/A | #N/A
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | Downloading reports of books | #N/A | #N/A | #N/A | #N/A | #N/A
14 | Viewing the transactions | #N/A | #N/A | #N/A | #N/A | #N/A
15 | Previewing the books' content | #N/A | #N/A | #N/A | #N/A | #N/A
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | Advertisement(Recommendation) | #N/A | #N/A | #N/A | #N/A | #N/A
18 | Adding book to my shopping cart | #N/A | #N/A | #N/A | #N/A | #N/A
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | Cancelling orders | #N/A | #N/A | #N/A | #N/A | #N/A
21 | Viewing the history of deal(progress status) | #N/A | #N/A | #N/A | #N/A | #N/A
22 | Setting up shipping address | #N/A | #N/A | #N/A | #N/A | #N/A
23 | Editing book's infomation(price) | #N/A | #N/A | #N/A | #N/A | #N/A
24 | Applying discount | #N/A | #N/A | #N/A | #N/A | #N/A
25 | Making comment | #N/A | #N/A | #N/A | #N/A | #N/A

## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | Creating my own online book shop | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | There should be a button for the users to create their own bookstore by redirecting them to a page which request them to input related information to create a bookstore. | Creating shops related page will be shown after a request, for instance, a user who register as a shop pwner, clicks the button 'create a shop' on the home page, then the system should redirect to another page or showing a dialog to collect the information of the shop the user want to create. The collecting inforamtion should be saved appropriately in the database. A valid bookstore should have at least a name.(Users: Shop Owner/Admins)
2 | Publishing a book in a shop | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | There should be a page showing the shops owned by the user as a list, which should be accessible on the home page. Admins will have a list of all shops existing on the homepage of the website currently. Users can select their shop and see/edit further infomation about the shop | The users can also upload few images about the book as cover or preview showing to the users, when entering the book's infomation.(Users: Shop Owner/Admins)
3 | Removing a book in a shop | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | There should be a page showing the shops owned by the user as a list, which should be accessible on the home page.Admins will have a list of all shops existing on the homepage of the website currently. Users can select their shop and remove it from their owning shops. | A dialog to confirm the user's operation should come up after the users click on the delete button on the specific owned shop. (Users: Shop Owner/Admins)
4 | Viewing a books' infomation | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Users select a book in the list by searching with keywords and then a page showing the books's details should be redirecting. | The page should at least include the book's name, Author, price, status ( available or not), place of dispatch, and buying/adding to the cart buttons.
5 | Viewing comments towards a book | Front-end Programmer/Back-end Programmer/Database Handler | Low | Big | On hold | Users can see the comments which made by the people who bought it before under the book's information. | Comments should be attached to the books details page.(Users: Admins/Shop owner/ Public user)
6 | Blocking user's account | Front-end Programmer/Back-end Programmer | Medium | Big | On hold | Administrator should be able to block/unblock a user's account. | Blocked users are recorded and cannot login during the block period.(Users: Shop owner/Public users)
7 | Downloading reports of books | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold
8 | Viewing the transactions | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold
9 | Previewing the books' content | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Users can see the preview contents of a book when they are viewing the detail of that book. | Preview contents should be attached to the books details page.(Users: Admin/public users/shop owners)
10 | Advertisement(Recommendation) | Front-end Programmer/Back-end Programmer | Medium | Big | On hold | Users can receive advertisements according to their interests. | Advertising should based on user habits.
11 | Adding book to my shopping cart | Front-end Programmer/Back-end Programmer | Medium | Big | On hold | Users are able to add a book to their shopping cart, and they can view the shopping cart on a specific page.
12 | Cancelling orders | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Users are able to cancel their order before the limit time. | Limit time should be 2 hours.
13 | Viewing the history of deal(progress status) | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Users can view a list of their deals and full history of each deal should also be able to show. | Deals containing both done deals and processing deals, and processing deals containing processing status of that deal.
14 | Setting up shipping address | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Users can setup their shipping address on website or filling deal details. | If user doesn't have a shipping detail, they are forced to fill that when they want to buy something. All shipping details of each user are stored for them to select.
15 | Editing book's infomation(price) | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Shop owners can edit their books' information. | A shop owner can and only can edit their own books on selling.
16 | Applying discount | Front-end Programmer/Back-end Programmer | Medium | Big | On hold | Users should be able to apply discount to a shop owner and shop owner can approve or disapprove.
17 | Making comment | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Users can making comments on a book after they have successfully bought a book. | Only users who successfully done a deal can comment on that book.
18 | Receiving notification | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Users can receive notifications from system. | Users: Admin/Public user/Shop owner, Notifications: e.g. discount, comment, problems, etc.
19 | Viewing about | Front-end Programmer | Medium | Big | On hold
20 | Approve application of register as a shop owner | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Administrators can approve or disapprove the apply from public users to be a shop owner. If approved, the public user should be updated to shop owner. | Public user can apply for being a shop owner, and Administrator can approve the apply.
21 | Paying for a book | Front-end Programmer/Back-end Programmer/Database Handler | Medium | Big | On hold | Users can pay after a dealing created. | If user refused to pay, the dealing is unsuccessful.
22 | Removing a book from my shopping cart | Front-end Programmer/Back-end Programmer | Medium | Big | On hold | Users can remove a book from their shopping cart after they added that book. | Removed book won't show again until user add that book again.
33
34
35
36
37
38
39
40